## Sheet1
| 1. Identification | 2. Analysis |  |  | 3. Mitigation |  |  |  | 4. Follow-up
# | Risk | Probability (1-5) | Consequence (1-5) | Risk before mitigation (1-25) | Mitigating measures | Probability (1-5) | Consequence (1-5) | Risk after mitigation (1-25) | Responsible | Due by | Status
1 | Flooding prevents the seminar from taking place as the roads to the village become inaccessible | 2 | 5 | 10 | •Have alternative venues | 2 | 3 | 6 |  | Identify alternative venues before rainy season
|  | Happens about once every ten years | Not possible to hold seminar |  | • Purchase off-road vehicles | Happens about once every ten years | Seminars held in alternative venues |  | Project manager
• …
2 | Trained mid-wives leave the country shortly after training instead of working in local clinics | 4 | 4 | 16 | • Participants sign contract to stay in their job minimum three years after training | 3 | 3 | 9 | Project manager develops contract | Contract prepared by 12.11.2017.
|  | About 30% of trained health workers have left country within the last five years | The project will have no effect on maternal health in the target community | [5 empty] | quality assured by legal department | Participants signed within first week of training
• …
3 | [Anti-corruption] | [probability] | [consequence] | #VALUE! | • | [probability] | [consequence] | #VALUE!
•
•
4 | [Women and gender equality] | [probability] | [consequence] | #VALUE! | • | [probability] | [consequence] | #VALUE!
•
•
5 | [Climate and environment] | [probability] | [consequence] | #VALUE! | • | [probability] | [consequence] | #VALUE!
•
•
6 | [Human rights] | [probability] | [consequence] | #VALUE! | • | [probability] | [consequence] | #VALUE!
•
•
7 |  | [probability] | [consequence] | #VALUE! | • | [probability] | [consequence] | 0
•
•
Note on L22: Expand the table by copying the final row